## Procurement schedule
Ngwedi Onderstepoort 1 – 220 MW: PCG procurement schedule re-forecast (award 15 Oct 2026; no site work before 2 Jan 2027)
Source: Draft Baseline Rev.00 (P6 .xer, data date 25 Aug 2026). Re-forecast by forward-pass CPM on the programme logic and Mon–Fri calendar. See Assumptions sheet. Dates = programme (early) dates.
Package | Item (PCG procurement) | Lead time PO→1st delivery (weeks) | PO / order date – baseline | PO / order date – REVISED | Slip (weeks) | Latest order date without delaying completion (uses float) | On site – first delivery (revised) | On site – last delivery (revised) | Installation start (revised) | Installation finish (revised) | Float to completion (wd, cap 250)
PV field | Screw/ground piles (6 × 36.6 MW batches) | 10.7 | 2027-04-12 | 2027-06-02 | 7.3 | 2027-07-01 | 2027-08-16 | 2027-11-30 | 2027-07-16 | 2028-02-01 | 20
PV field | Tracker structures (6 batches) | 11.6 | 2027-04-26 | 2027-06-17 | 7.4 | 2027-07-07 | 2027-09-06 | 2028-01-27 | 2027-09-07 | 2028-02-24 | 14
PV field | PV modules (6 procurement batches) | 12.9 | 2027-04-23 | 2027-06-15 | 7.6 | 2027-07-08 | 2027-09-13 | 2028-03-09 | 2027-09-17 | 2028-04-13 | 16
PV field | Inverters (2 batches) | 21.6 | 2027-04-02 | 2027-05-13 | 5.9 | 2027-09-03 | 2027-10-11 | 2027-11-08 | 2027-12-21 | 2028-03-09 | 79
PV field | Power stations (MV skids / transformers) | 29.9 | 2027-03-17 | 2027-04-30 | 6.3 | 2027-06-02 | 2027-11-25 | 2027-11-25 | 2027-11-26 | 2027-12-29 | 23
PV field | MV cable | 10.1 | 2027-06-01 | 2027-07-12 | 5.9 | 2027-08-31 | 2027-09-21 | 2027-10-13 | 2027-09-22 | 2028-01-04 | 35
PV field | LV cable | 14.3 | 2027-06-01 | 2027-07-12 | 5.9 | 2027-11-19 | 2027-10-20 | 2027-11-10 | 2028-01-28 | 2028-05-04 | 92
PV field | DC cable (string cable) | 12.1 | 2027-07-15 | 2027-09-06 | 7.6 | 2027-09-06 | 2027-11-30 | 2027-12-22 | 2028-01-21 | 2028-09-04 | 0
PV field | Optical fibre cable (PV area) | 12.3 | 2027-06-23 | 2027-08-02 | 5.7 | 2028-05-11 | 2027-10-27 | 2027-11-17 | 2028-01-19 | 2028-04-12 | 194
PV field | Earthing materials | 10.1 | 2027-05-24 | 2027-07-14 | 7.3 | 2027-11-26 | 2027-09-23 | 2027-10-22 | 2027-10-25 | 2028-06-09 | 95
PV field | NCU (network control units) | 17.9 | 2027-05-31 | 2027-07-09 | 5.6 | 2027-12-13 | 2027-11-11 | 2027-11-11 | 2027-11-11 | 2028-05-09 | 109
PV field | TCU (tracker control units) | 17.9 | 2027-06-03 | 2027-07-14 | 5.9 | 2027-10-20 | 2027-11-16 | 2027-11-16 | 2027-11-17 | 2028-06-12 | 68
PV field | Weather stations | 16.3 | 2027-05-26 | 2027-07-06 | 5.9 | 2028-01-10 | 2027-10-28 | 2027-10-28 | 2027-11-12 | 2028-05-15 | 130
PV field | PPC & SCADA system | 15.9 | 2026-12-18 | 2026-12-31 | 1.9 | 2027-11-19 | 2027-04-21 | 2027-04-21 | 2027-11-19 | 2028-02-24 | 223
IPP substation (132/33 kV) | Main transformer 145 MVA 33/132 kV | 37.4 | 2026-11-18 | 2026-11-30 | 1.7 | 2027-05-13 | 2027-08-19 | 2027-08-19 | 2027-08-20 | 2027-10-15 | 111
IPP substation (132/33 kV) | 132 kV plant: SF6 breaker, isolators, CT, VT, busbar, arresters | 19 | 2026-11-18 | 2026-11-30 | 1.7 | 2027-07-29 | 2027-04-12 | 2027-07-07 | 2027-07-28 | 2027-08-19 | 165
IPP substation (132/33 kV) | 33 kV switchgear, station transformer, NECRT | 19 | 2026-11-18 | 2026-11-30 | 1.7 | 2027-08-13 | 2027-04-12 | 2027-05-25 | 2027-07-14 | 2027-12-17 | 175
IPP substation (132/33 kV) | 132 kV & 33 kV power cables/accessories | 12.3 | 2026-11-18 | 2026-11-30 | 1.7 | No constraint (>250 wd float) | 2027-02-24 | 2027-02-24 | 2027-08-12 | 2028-01-11 | 250
IPP substation (132/33 kV) | Protection, control, comms, metering, DFR, SCADA, DC & fire systems | 12.1 | 2026-12-15 | 2026-12-29 | 2 | 2027-07-23 | 2027-03-24 | 2027-06-22 | 2027-11-19 | 2028-05-15 | 142
IPP substation (132/33 kV) | Earthing materials | 9 | 2026-12-15 | 2026-12-29 | 2 | 2027-02-19 | 2027-03-02 | 2027-03-02 | 2027-09-09 | 2027-10-01 | 37
Switching station (132 kV) | 132 kV plant (breaker, disconnectors, CT/PT, busbar, arresters) & 132 kV cables | 13.7 | 2026-11-24 | 2026-12-04 | 1.4 | 2027-05-12 | 2027-03-10 | 2027-07-13 | 2027-06-11 | 2027-11-26 | 106
Switching station (132 kV) | Protection, comms, metering, DC & control cables | 13.7 | 2026-11-24 | 2026-12-04 | 1.4 | 2027-06-30 | 2027-03-10 | 2027-06-08 | 2027-06-11 | 2028-04-03 | 140
Overhead line (132 kV) | Tower steel (galvanised angle) | 31.1 | 2026-12-11 | 2026-12-24 | 1.9 | 2027-03-08 | 2027-07-30 | 2027-07-30 | 2027-08-02 | 2027-12-13 | 50
Overhead line (132 kV) | Conductor, earthwire, OPGW | 19 | 2026-12-11 | 2026-12-24 | 1.9 | 2027-08-02 | 2027-05-06 | 2027-06-18 | 2028-01-13 | 2028-02-15 | 150
Overhead line (132 kV) | Hardware, insulators, earthing | 9.1 | 2026-12-11 | 2026-12-24 | 1.9 | 2027-09-14 | 2027-02-26 | 2027-05-06 | 2027-11-16 | 2028-04-12 | 180
Hera MTS (Eskom 400/275 kV) | 800 MVA main transformer | 64.1 | 2026-10-23 | 2026-11-04 | 1.7 | 2026-12-11 | 2028-01-27 | 2028-01-27 | 2028-01-28 | 2028-04-18 | 27
Hera MTS (Eskom 400/275 kV) | 275 & 400 kV breakers, disconnectors, CT, earth switches, arresters | 18.7 | 2026-12-24 | 2027-01-07 | 2 | 2027-07-14 | 2027-05-18 | 2027-09-23 | 2027-05-05 | 2028-05-25 | 129
Hera MTS (Eskom 400/275 kV) | Station transformer, 22 kV arrester, insulators | 12.3 | 2026-10-23 | 2026-11-04 | 1.7 | 2027-11-02 | 2027-01-29 | 2027-05-18 | 2027-05-05 | 2028-05-25 | 249
Hera MTS (Eskom 400/275 kV) | 50 kA upgrade items (disconnectors, CT, earth switches, pole insulators) | 12.3 | 2026-10-23 | 2026-11-04 | 1.7 | 2027-09-09 | 2027-01-29 | 2027-06-10 | 2027-05-05 | 2028-05-25 | 212
Hera MTS (Eskom 400/275 kV) | Protection scheme, comms, remote control, junction boxes | 18.3 | 2026-10-23 | 2026-11-04 | 1.7 | 2027-09-27 | 2027-03-12 | 2027-04-29 | 2027-05-19 | 2028-06-23 | 223
Hera MTS (Eskom 400/275 kV) | Power/control cables & earthing | 9.3 | 2026-10-23 | 2026-11-04 | 1.7 | 2027-11-01 | 2027-01-08 | 2027-01-29 | 2027-05-05 | 2028-05-25 | 248
Ngwedi MTS | Primary plant (breakers, disconnectors, earth switches, CT, VT, arresters, insulators, busbar) | 12.3 | 2026-11-04 | 2026-11-16 | 1.7 | 2027-05-11 | 2027-02-10 | 2027-04-12 | 2027-07-05 | 2027-10-28 | 119
Ngwedi MTS | Feeder protection, control cable, terminations, JBs | 5.6 | 2026-10-14 | 2026-10-26 | 1.7 | 2027-08-16 | 2026-12-04 | 2027-03-10 | 2027-10-22 | 2028-02-14 | 201
Ngwedi MTS | Civil materials (steel/gantry, cement, earthing, trench) | 4.3 | 2026-12-02 | 2026-12-14 | 1.7 | No constraint (>250 wd float) | 2027-01-13 | 2027-02-17 | 2027-05-11 | 2027-08-04 | 250

## Key dates
Milestone | Baseline | Revised | Shift (calendar days)
Contract award (assumed baseline = P6 data date) | 2026-08-25 | 2026-10-15 | 51
PV design award (A1110) | 2026-09-21 | 2026-10-30 | 39
Early-work complete (A1120) | 2026-11-17 | 2027-01-11 | 55
NTP issued (A15750) | 2026-11-18 | 2027-01-12 | 55
Pull-out test rig mobilised on site (A2250 finish) | 2026-11-24 | 2027-01-18 | 55
Pull-out test report approved (A2300) | 2027-01-28 | 2027-03-19 | 50
Unconditional approval Sch.07 plans (A15300) | 2026-12-15 | 2027-02-08 | 55
Site establishment 100% (A15310) | 2027-03-31 | 2027-05-21 | 51
75% IFC drawings (A15320) | 2027-05-18 | 2027-06-28 | 41
Major earthworks complete (A15330) | 2027-02-26 | 2027-04-22 | 55
25% piles installed (A15360) | 2027-08-24 | 2027-10-14 | 51
25% trackers installed (A15370) | 2027-09-10 | 2027-11-02 | 53
25% PV modules installed (A15390) | 2027-09-29 | 2027-11-18 | 50
25% OHL towers installed (A15400) | 2027-10-21 | 2027-11-08 | 18
IPP substation foundations 100% (A15410) | 2027-07-29 | 2027-08-11 | 13
Major civil works complete (A15350) | 2027-12-09 | 2028-02-01 | 54
Mechanical completion substation & Eskom self-build (A15340) | 2028-06-09 | 2028-06-28 | 19
First section ready for energisation (A15420) | 2028-06-09 | 2028-06-28 | 19
First synchronisation / energisation (A15430) | 2028-08-03 | 2028-09-26 | 54
Commercial Operations Date (A16730) | 2028-10-03 | 2028-11-21 | 49
Taking-Over Certificate (A16740) | 2028-10-31 | 2028-12-20 | 50
Handover certificate (A15690) | 2028-10-31 | 2028-12-20 | 50

## Assumptions
ASSUMPTIONS AND METHOD
1. Source file: 'Ngwedi Onderstepoort 1 220MW Solar Power Project(Draft Baseline Rev.00).xer' – 1,916 activities, 2,916 relationships, calendar Mon–Fri 8 h with 22 listed public holidays.
2. Re-forecast engine reproduces the file's own early dates for 1,904 of 1,916 activities (the 12 differences are 1-day rounding on short hot-commissioning tests, not relevant to procurement).
3. Baseline award date taken as 25 Aug 2026 (P6 data date; all 11 start activities begin there). Revised award 15 Oct 2026: all early-work activities restart no earlier than 15 Oct 2026.
4. Grid-works design: treated as already appointed – activity A1010 held complete on 2 Oct 2026, design activities start 5 Oct 2026. [Assumption – confirm actual start]. If grid design cannot start until award (15 Oct) the 800 MVA Hera transformer order slips ~6 weeks (see summary).
5. PV design award: finishes 30 Oct 2026 ('end of October').
6. Site restriction: every Construction, Commissioning and Pre-NTP site activity (pull-out test, temporary facilities, access road) constrained to start no earlier than 2 Jan 2027 (first working day Mon 4 Jan 2027; 1 Jan is a holiday). Deliveries of materials and off-site procurement are not constrained.
7. Payment-milestone dates (fixed 'finish-on' constraints in the file) were released so they follow the re-forecast logic; they are not contractual dates and need to be renegotiated with the Employer.
8. 'PO / order date' for PV-field packages = finish of the programme's 'PO Issue / PO Placed' activity (technical freeze happens before it). For grid-works packages the programme models PO-to-delivery as one lead-time activity, so order date = start of that activity and delivery = its finish.
9. 'On site' dates = completion of 'Site receive & inspection' (PV) or end of the lead-time activity (grid). Installation windows are the min start / max finish of the matching construction activities (all blocks). Pile window includes pre-drilling, which precedes first pile delivery.
10. Float = total float (working days) to the revised project finish with payment-milestone constraints removed; indicative only.
11. Excluded: fencing, roads, O&M building, security, temporary facilities (subcontract/civil scope, not equipment procurement). No Christmas shutdown is modelled in the programme calendar beyond public holidays.